## Sheet1
User Story | Story Points | Average speed per team member | People on the team | Team Velocity | Sprints | Days
Login doesn’t work | 5 | 6 | 4 | 22 | 9 | 45
Login UI issue in Safari | 3 |  | 5 | 30 | 7 | 35
Login UI issues in FireFox | 3 |  | 3 | 18 | 11 | 55
BackEnd users login validation logic changes | 13
UI Create New Login Form | 13
Editing account data when created an account | 8
Implement Facebook Registration | 5
Implement User Registration with Google Account | 5
Users need to attach credit cards to their accounts | 21
Users required password logic changes | 3
Credit cards validation issues | 5
User can edit profile picture | 1
User can upload profile picture | 3
User can delete a publication | 3
User can publish new content | 5
Adding Categories and tags for the users contents | 8
Private data restrictions | 8
User can reset the password | 5
User can Register in the platform | 13
Users can share content with other users | 5
Users can delete their account | 5
Users need to import files | 13
Users need to export files | 8
Schedule functionality | 21
Total Story Points | 182